## Dashboard
Free template made by and provided by contentworkflow.co
| VIDEO PRODUCTION TRACKER | [5 empty] | CHOOSE CLIENT ➤ | ALL |  | CHOOSE EDITOR ➤ | ALL
[7 empty] | CHOOSE STATUS ➤ | ALL |  | CHOOSE PRIORITY ➤ | ALL
| VIDEOS | BILLED | EDITOR COST | MARGIN | OVERDUE | IN CLIENT REVIEW
| VIDEO | CLIENT | PROJECT | STATUS | PRIORITY | EDITOR | VERSION | DEADLINE | PUBLISH DATE | PRICE | EDITOR COST | MARGIN

## Add Content
Free template made by and provided by contentworkflow.co
VIDEO | CLIENT | PROJECT | TYPE | PLATFORM | STATUS | PRIORITY | EDITOR | VERSION | DEADLINE | RECORDING DATE | REVIEW DUE | PUBLISH DATE | RUNTIME | ASPECT | PRICE | EDITOR COST | MARGIN | FILE LOCATION | NOTES
Launch teaser, 30s | Acme Media | September launch | Shortform | Instagram | Client Review | High | Alex | v3 | 2026-09-07 | 2026-08-21 | 2026-09-01 | 2026-09-12 | 0:30 | 9:16 | 65 | 25 |  | Drive / Acme / September launch / Teaser / v3 | Client has v3, notes due Friday.
Founder interview, full cut | Acme Media | September launch | Long-form | YouTube | Editing | Normal | Alex | v2 | 2026-09-13 | 2026-08-21 | 2026-09-09 | 2026-09-17 | 14:20 | 16:9 | 250 | 90 |  | Drive / Acme / September launch / Interview / v2 | Chapters still to add.
Podcast clip 04 | Northwind Coffee | Podcast clips, batch 7 | Shortform | TikTok | Approved | Normal | Sam | v1 | 2026-08-31 | 2026-08-12 | 2026-08-26 | 2026-09-05 | 0:52 | 9:16 | 50 | 20 |  | Drive / Northwind / Batch 7 / Clip 04 / v1 | Approved first pass.
Product demo, 60s | Blue Harbor Gym | Website refresh | Shortform | Instagram | Filming | Urgent | Sam |  | 2026-09-02 | 2026-09-04 | 2026-09-10 | 2026-09-15 | 1:00 | 16:9 | 120 | 45 |  |  | Footage arrives tomorrow. Deadline already slipped once.
Testimonial, 30s cut | Blue Harbor Gym | Website refresh | Shortform | Facebook | Published | Low | Alex | v4 | 2026-08-14 | 2026-08-05 | 2026-08-11 | 2026-08-19 | 0:31 | 9:16 | 65 | 25 |  | Drive / Blue Harbor / Website refresh / Testimonial / v4 | Four rounds. Quote the next one higher.

## Settings
Free template made by and provided by contentworkflow.co
CLIENTS | EDITORS | HOW THIS TAB WORKS
Acme Media | Alex | Type your clients in column B and your editors in column E, one per row.
Northwind Coffee | Sam | Both lists feed the dropdowns on Add Content and the filters on Dashboard.
Blue Harbor Gym |  | Ten slots each; insert rows inside the list if you need more.
Statuses, priorities and types are fixed: they mirror the ContentWorkflow pipeline.

## DATA (hidden)
ALL | ALL | ALL | ALL | Shortform | Instagram | 9:16
|  | Ideas | Low | Long-form | TikTok | 16:9
|  | Scripting | Normal | Carousel | YouTube | 1:1
|  | Filming | High | Image post | Facebook | 4:5
|  | Editing | Urgent |  | Snapchat
|  | Internal Review |  |  | Twitter
|  | Client Review |  |  | Reddit
Revision
Approved
Scheduled
Published
Archive